## Sprint #1
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 40 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2019-04-29 | 2019-04-30 | 2019-05-01 | 2019-05-02 | 2019-05-03 | 2019-05-04 | 2019-05-05 | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09 | 2019-05-10 | 2019-05-11 | 2019-05-12
|  |  |  | 160 | 148 | 136 | 124 | 112 | 100 | 88 | 60 | 42 | 30 | 12 | 0 |  |  | Ideal Burndown
|  |  | 160 | 158 | 152 | 140 | 123 | 113 | 103 | 56 | 40 | 8 | 0 | 0 | 0 | 0 | 0 | Remaining Hrs (Total)
Enable Add Card API to allows users to add and manage starbucks cash cards | Design Business Logic | Julian Simon | 15 | 2019-04-29: 15; 2019-04-30: 12; 2019-05-01: 9; 2019-05-02: 7; 2019-05-03: 4; 2019-05-04: 3; 2019-05-05: 2; 2019-05-06: 1
| Implement Back-End Code | Julian Simon | 15 | 15 | 15 | 12 | 12 | 10 | 7 | 2 | 2 | 1
| Complete Unit Testing | Julian Simon | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0
| Complete Regression Testing | Julian Simon | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 2 | 0
| Write Documentation | Julian Simon | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
API to Manage Order where loged in user will try to see the History of the Order placed | Design Business Logic | Sandhya Gadgoli | 18 | 18 | 16 | 15 | 12 | 10 | 7 | 4 | 2 | 0
| Implement Back-End Code | Sandhya Gadgoli | 12 | 12 | 10 | 10 | 8 | 5 | 5 | 3 | 2 | 1
| Complete Unit Testing | Sandhya Gadgoli | 2 | 2019-04-29: 2; 2019-04-30: 2; 2019-05-01: 2; 2019-05-02: 2; 2019-05-03: 1; 2019-05-04: 1; 2019-05-05: 1; 2019-05-06: 0
| Complete Regression Testing | Sandhya Gadgoli | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 3 | 2 | 0
| Write Documentation | Sandhya Gadgoli | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 0
Enable User Creation API and user authentication to allow users to login and items from the menu and place an order | Design and Implement Business Logic | Paramdeep Saini | 12 | 12 | 10 | 12 | 12 | 6 | 3 | 3 | 2 | 0
| Implement Back-End Code | Paramdeep Saini | 12 | 12 | 11 | 7 | 6 | 5 | 4 | 3 | 3 | 2 | 0
| Complete Unit Testing | Paramdeep Saini | 6 | 2019-04-29: 6; 2019-04-30: 6; 2019-05-01: 6; 2019-05-02: 5; 2019-05-03: 2; 2019-05-04: 2; 2019-05-05: 2; 2019-05-06: 0
| Complete Regression Testing | Paramdeep Saini | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 0
| Write Documentation | Paramdeep Saini | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 1 | 0
Implement Payment API for users to make Payment for their order using their registered card. | Design Business Logic | Viswa Kambam | 12 | 12 | 12 | 12 | 6 | 4 | 4 | 3 | 1 | 0
| Implement Back-End Code | Viswa Kambam | 13 | 13 | 13 | 8 | 6 | 5 | 4 | 4 | 2 | 0
| Complete Unit Testing | Viswa Kambam | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 2 | 0
| Complete Regression Testing | Viswa Kambam | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 2 | 2 | 0
| Write Documentation | Viswa Kambam | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 0
Merge the controller and test the REST services with application flow
Prepare for presentaion, documentation, demonstration PPT etc
Team:
Paramdeep Saini | 20 hours / Week
Julian Simon | 20 hours / Week
Sandhya Gadgoli | 20 hours / Week
Viswa Kambam | 20 hours / Week
Total Available Hours During Sprint: | 160 hours